## Slide 1
Monday Meeting Prep
Sprint 3 Status · Doug Farewell · Quarterly Priorities
April 13, 2026
Konvoy Kegs · Katch Cloud Engineering
1 / 10
Notes: TITLE SLIDE - Welcome everyone, thanks for making time on a Monday - Three things to cover today: where Sprint 3 stands after the NS breach, Doug's handover, and a check-in on our quarterly priorities - This is Doug's last meeting with leadership so we want to make sure we capture everything we need from him

## Slide 2
Agenda
1
Doug's Legacy
47 closed tickets, 10 open for handover
2
Sprint 3 Velocity
NS breach impact, what's actually moved
3
Current Assignments
What's underway, what's blocked
4
Quarterly Priorities
Fuel Levy · Orders Experience · Refills
5
Backlog & Grouping
45 unassigned items, grouping opportunities
6
Doug Handover Checklist
Must-dos before Monday close
7
Recommended Actions
7 decisions for Monday
Konvoy Kegs · Katch Cloud Engineering
2 / 10
Notes: AGENDA - 7 items to get through — should take about 20-25 minutes - We'll start with recognising Doug's work, then move into sprint health - The back half is forward-looking: quarterly priorities, backlog triage, and actions we need agreement on today

## Slide 3
Doug's Legacy — Orders Frontend
47
Issues Closed
10
Still Open
6
Months Tenure
Key Deliverables
Orders table, routing, CRUD, scheduling
Order pricing, invoicing, charts
Filtering, exports, internal notes
YoY comparison charts
Organisation side panel & orders list
Mobile responsive forms
Collections UI + scheduling
Feature flag system for orders
Handover: 10 tickets need reassignment — lease decoupling (#4526) needs special discussion with Doug
Konvoy Kegs · Katch Cloud Engineering
3 / 10
Notes: DOUG'S LEGACY - Doug closed 47 issues over ~6 months — he essentially built the entire Orders frontend from scratch - The big items: orders table, create/view/edit/cancel/schedule flows, pricing, invoicing, charts, filtering, exports - He also built the year-over-year comparison charts, organisation side panel, mobile forms, and the feature flag gating system HANDOVER CONCERNS: - 10 tickets still assigned to him — need to reassign today - The big one is #4526 (decouple leases from orders) — this is architecturally complex and Doug has context nobody else has - 3 Rainforest QA E2E test tickets (#4473-4475) could be grouped into one effort for Bea - #4636 (remove rolled-out feature flags) is a good starter ticket for Bea — low risk, gets her a quick first PR

## Slide 4
Sprint 3 Velocity — NS Breach Impact
Week 1 lost to NS breach recovery — 16 of 19 closed items were Rob's breach/audit work
19
Items Closed
(since Apr 3)
16
Rob — 12 Breach
+ 4 NS Audit
0
Planned Goals
Completed
7
Working Days
Remaining
Sprint Comparison
Sprint 2: 47 items closed in 2 weeks (13 in final week alone)
Sprint 3: Effectively a 1-week sprint for planned work
Key risk: Day 8 scope freeze approaching with zero goal progress
Konvoy Kegs · Katch Cloud Engineering
4 / 10
Notes: SPRINT 3 VELOCITY — NS BREACH IMPACT - The honest truth: Week 1 of Sprint 3 was completely consumed by the NetSuite security breach - 19 items closed since Apr 3. I personally closed 16 — 12 reactive breach fixes (auth failures, subsidiary mismatches, invoice backfill 404s, phone sanitisation, observability) plus 4 NS Audit security items on Apr 12 (token revocation, new integration role, service account, token regeneration) - Millicent closed 2 bug fixes (contract brewer order/transfer date issues) - Doug closed 1 (Safari button fix) and Bea hasn't closed any yet — she's still ramping up, which is expected - The good news: the NS Audit TBA rotation is now fully complete. The 8 remaining audit tasks (docs, SSM rotation, EKS logging, OAuth planning) are assigned to me and can be timeboxed going forward THE NUMBERS: - Sprint 2 did 47 items in 2 weeks for comparison - Zero planned Sprint 3 goals have been completed — no Fuel Levy progress, no review backlog cleared - We have 7 working days left and Day 8 scope freeze is approaching (Thursday) - Effectively this is a 1-week sprint for any planned work QUESTION FOR LEADERSHIP: Do we extend Sprint 3 by a week to account for the breach, or accept reduced output and carry forward?

## Slide 5
Team Load & Current Assignments
Person | Open | Sprint | Focus This Sprint | Status
Rob | 53 | 9 | FL-5, FL-6, breach done, 8 audit items remain | Overloaded
Millicent | 30 | 5 | Scheduled order updates, bug fixes, chores | Capacity
Bea | 33 | 12 | FL frontend (blocked), Orders UX tickets | Ramping
Doug | 10 | 7 | All need reassignment before departure | Departing
Unassigned | 45 | — | Includes FL-1 to FL-4 blockers + 28 design tickets | Needs triage
Key issue: Rob has 53 open issues (incl 8 NS Audit) — sustainable is ~22 SP/sprint. Millicent has capacity to absorb FL backend tickets. Bea's 12 sprint items need trimming to 3–4 realistic targets.
Konvoy Kegs · Katch Cloud Engineering
5 / 10
Notes: TEAM LOAD & ASSIGNMENTS - I'm at 53 open issues — sustainable is around 22 SP per sprint. This is the main risk to the team right now. - 8 of those 53 are remaining NS Audit tasks (docs, SSM rotation, EKS logging, credential redaction, OAuth planning) — the urgent TBA rotation is done but these still need timeboxing - Millicent is at 30 but has capacity — she's the right person to absorb Fuel Levy backend tickets (FL-1 to FL-3) - Bea has 33 total but 12 in the current sprint, which is too many for someone onboarding. Recommend trimming to 3-4 realistic targets - Doug's 7 sprint items all need reassignment before he leaves — that's a decision we need to make today - 45 unassigned items include critical FL blockers and the 28 design-feedback tickets from the recent review KEY POINT: Millicent has capacity. She should take on FL backend work immediately. KEY POINT: Bea needs fewer items, not more. Focus her on quick wins to build confidence. KEY POINT: NS Audit urgent items are done — remaining 8 tasks can be paced across sprints.

## Slide 6
Quarterly Priorities — Status Check
Fuel Surcharge
Behind
14 tickets total. FL-1 to FL-4 (backend foundation) are unassigned and block everything. Rob's FL-5/FL-6 and all of Bea's frontend work are waiting.
Action: Assign FL-1 to FL-3 to Millicent now
Orders Experience
Progressing
Doug built the core (47 tickets). Bea owns the epic. 28 new design-feedback tickets in backlog need triage. 3 new sub-epics created for UX improvements.
Action: Triage design-feedback batch — pick 3–5 for Sprint 4
Refills in Cloud
Not Started
6 sub-tickets under NS Epic 1. Discovery (#4309) sitting since Sprint 1. Depends on NS Epic 0 Foundation which is also still open.
Action: Rob to complete NS-1.1 discovery this sprint
Konvoy Kegs · Katch Cloud Engineering
6 / 10
Notes: QUARTERLY PRIORITIES — STATUS CHECK 1. FUEL SURCHARGE (Behind) - This is the #1 business priority from CEO/COO - 14 tickets total. The problem: FL-1 through FL-4 (the backend foundation) are UNASSIGNED - My FL-5 (CRUD API) and FL-6 (NS invoice integration) are blocked until FL-2 and FL-3 are done - All of Bea's frontend work (FL-7 to FL-10) is blocked on the backend being complete - DECISION NEEDED: Assign FL-1 to FL-3 to Millicent today. This unblocks the entire chain. 2. ORDERS EXPERIENCE (Progressing) - Doug built the core — 47 tickets of foundation work. Bea now owns the epic (#4377) - 28 new design-feedback tickets landed in backlog from a recent design review session - 3 new sub-epics created: Rentals List improvements, Rental Form improvements, Order Detail improvements - These are good ideas but they're scope creep risk — we need to pick 3-5 for Sprint 4 and park the rest 3. REFILLS IN CLOUD (Not Started) - 6 sub-tickets under NS Epic 1. The discovery ticket (#4309) has been sitting since Sprint 1 - It depends on NS Epic 0 Foundation (#4296) which is also still open - I need to complete the NS-1.1 discovery this sprint to unblock Millicent on the implementation tickets - Realistic timeline for full implementation: Sprint 4-5

## Slide 7
Backlog — 45 Unassigned Items
Natural groupings identified for batch triage:
28
Design Feedback
All created Apr 7 from one design review. 3 epics: Rentals List (11), Rental Form (8), Order Detail (9). 23 higher-priority, 5 low-priority.
0
NS Audit
All 4 unassigned items closed Apr 12 (TBA rotation complete). 8 remaining audit tasks assigned to Rob.
4
Fuel Levy Backend
FL-1 to FL-4 — critical blockers. Assign to Millicent.
3
NetSuite
Rental order table error (#4623), item mapping (#4622), billing backpopulate (#4176).
2
Bugs & Chores
SignupForm email unused, consolidate default tenant.
8
Other
Cutover, cutoff time, unschedule endpoint, global search perf, collection blind spot + 3 misc.
Konvoy Kegs · Katch Cloud Engineering
7 / 10
Notes: BACKLOG — 45 UNASSIGNED ITEMS (down from 48 — NS Audit items complete) - These cluster into natural groups, which makes triage much easier DESIGN FEEDBACK (28 items): - All 28 were created on April 7 from a single design review session — so they're all the same age - They sit under 3 parent epics: * Rentals List Page (#4587) — 11 tickets: default filters, column config, saved searches, SKU layout, market filter * Rental Order Form (#4598) — 8 tickets: merge customer/producer field, transport toggle, SKU display, pricing declutter * Order Detail & Workflow (#4606) — 9 tickets: order editing (scheduled + completed), role-based permissions, UI tidy-ups - 23 are higher-priority, 5 tagged low-priority (mostly UI cosmetics in Order Detail) - The Order Detail epic has the meatiest items: #4607-4609 (editing orders + permissions) — those touch backend too - RECOMMENDATION: Triage by epic. Rentals List and Rental Form are pure frontend — good for Bea once she's up to speed. Order Detail has backend dependencies so park those for now. NS AUDIT (0 unassigned — COMPLETE from backlog perspective): - All 4 previously unassigned items closed on Apr 12: #4536 (revoke tokens), #4537 (integration role), #4538 (service account), #4539 (new tokens) - The TBA token rotation is fully done — this was the urgent security work - 8 remaining audit tasks are all assigned to Rob: documentation (#4533), pre-release investigation (#4534), role permissions check (#4535), SSM/DB token rotation (#4540), EKS audit logging (#4541), credential redaction (#4542), non-NS credential rotation (#4543), OAuth 2.0 planning (#4544) - These are important but not urgent — recommend timeboxing at 2-3 SP per sprint FUEL LEVY BACKEND (4 unassigned): - FL-1 to FL-4 — still the critical blockers. Same message: assign to Millicent. NETSUITE (3 items): - #4623 rental_order table not found, #4622 missing item mapping, #4176 billing emails backpopulate - The first two are post-rollback cleanup issues BUGS & CHORES (2 items): - #4213 SignupForm email unused, #3928 consolidate default tenant - Low priority, good for a quiet sprint day OTHER (8 items): - Order Experience Cutover (#4174), cutoff time (#4088), unschedule endpoint (#4108), global search perf (#4250), collection blind spot (#4385) + 3 misc items - #4250 (global search 11+ seconds) is worth flagging — it's a user-facing performance issue

## Slide 8
Doug Handover — Monday Checklist
Must
Confirm all 10 open tickets are documented for Bea to pick up
Must
Deep-dive on #4526 (lease decoupling) — architecturally complex
Must
Rainforest QA test access and credentials documented
Must
Handover recordings confirmed in SharePoint
Ask
Undocumented tribal knowledge about Orders frontend state management?
Nice
Group 3 Rainforest QA tickets (#4473-4475) into single effort for Bea
Do
Reassign #4636 (feature flag cleanup) to Bea — good starter ticket
Konvoy Kegs · Katch Cloud Engineering
8 / 10
Notes: DOUG HANDOVER CHECKLIST - This is the practical stuff we need to nail before Doug walks out MUST DO: 1. Confirm all 10 open tickets have enough detail for Bea — descriptions, acceptance criteria, any gotchas 2. Deep-dive on #4526 (lease decoupling) — this is the biggest risk. It's architecturally complex and touches how orders and leases are structured. If Doug doesn't explain this, we'll lose weeks figuring it out 3. Rainforest QA test access — make sure credentials and setup docs are in the wiki/SharePoint 4. Handover recordings in SharePoint → Development → Recordings — confirm they're all there and watchable ASK DOUG: - Is there any undocumented knowledge about the Orders frontend state management? Any quirks, workarounds, or "don't touch this" areas that aren't in the code comments? NICE TO HAVE: - Group the 3 Rainforest QA tickets into one effort — they're related and Bea can tackle them together - Reassign #4636 (feature flag cleanup) to Bea right now — it's a perfect first ticket, low risk, well-defined

## Slide 9
Recommended Actions
1
Reassign Doug's 10 tickets — 7 to Bea, 3 QA tickets grouped
2
Assign FL-1 to FL-4 to Millicent — unblock Fuel Levy chain
3
Timebox remaining 8 NS Audit items — agree budget (e.g. 2–3 SP/sprint)
4
Clean Sprint 1 milestone — move or close 10 stale items
5
Triage design-feedback batch — pick 3–5 for Sprint 4, backlog rest
6
Rob scope reduction — 53 open items unsustainable, defer 10+
7
Revised Sprint 3 goals for remaining 7 days:
Rob: FL-5, FL-6, #4477, #4436, NS-1.1 discovery
Millicent: Start FL-1/FL-2, ship #4586, fix #4567
Bea: First PR merged (#4636 or #4498), start #4565 and #4369
Konvoy Kegs · Katch Cloud Engineering
9 / 10
Notes: RECOMMENDED ACTIONS — DECISIONS NEEDED TODAY 1. Reassign Doug's 10 tickets — suggest 7 to Bea (all frontend), 3 QA tickets grouped as one effort 2. Assign FL-1 to FL-4 to Millicent — this is the single most important action. It unblocks the entire Fuel Levy feature chain 3. Timebox remaining NS Audit — good news is the urgent TBA rotation is done (4 items closed Apr 12). But 8 audit tasks remain on my plate (docs, SSM rotation, EKS logging, credential redaction, OAuth planning). Need leadership to agree on a budget, e.g. 2-3 SP per sprint, so it doesn't compete with quarterly priorities 4. Clean Sprint 1 milestone — 10 items still sitting there from mid-March. Move to current sprint or close 5. Triage design-feedback batch — 28 tickets from design review. Pick 3-5 high-impact for Sprint 4, park the rest 6. My scope reduction — 53 open items is not sustainable. I need to identify 10+ items to defer or delegate. Would appreciate leadership input on what to deprioritise 7. Revised Sprint 3 goals given the lost week: - Rob: FL-5, FL-6, fix null billing emails (#4477), upgrade mailchimp (#4436), NS-1.1 discovery - Millicent: Start FL-1/FL-2, ship scheduled order updates (#4586), fix Twig error (#4567) - Bea: Get first PR merged (#4636 or #4498), then start consignment visibility (#4565) and email indicator (#4369)

## Slide 10
“
Ah, breaker one-nine, this here's the Rubber Duck...
Doug — you built the road we're all driving on now. 47 tickets, an entire Orders frontend, and the foundation this team will build on for years.
Time to set off on a new highway of discovery.
"We got a great big convoy, rockin' through the night" — C.W. McCall, Convoy (1978)
10 / 10
Notes: DOUG'S FAREWELL - Take a moment to acknowledge Doug's contribution - He joined when Orders was just a concept and built the entire frontend from the ground up - 47 closed tickets in 6 months — the orders table, every CRUD flow, charts, filters, invoicing, mobile forms - The foundation Bea and the team will be building on for the foreseeable future - The Convoy reference: the cofounders named the company after the 1978 movie — felt right to send Doug off on his own convoy - Wish him well on whatever comes next — he's earned it