## Slide 1
Monday Meeting Prep
Sprint 3 Status · Doug Farewell · Quarterly Priorities
April 13, 2026 · Katch Cloud Engineering
1 / 9

## Slide 2
Agenda
1
Doug's Legacy
47 closed tickets, 10 open for handover
2
Sprint 3 Velocity
NS breach impact, what's actually moved
3
Current Assignments
What's underway, what's blocked
4
Quarterly Priorities
Fuel Levy · Orders Experience · Refills
5
Backlog & Grouping
48 unassigned items, grouping opportunities
6
Recommended Actions
7 decisions for Monday
Konvoy Kegs · Katch Cloud Engineering
2 / 9

## Slide 3
Doug's Legacy — Orders Frontend
47
Issues Closed
10
Still Open
6
Months Tenure
Key Deliverables
Orders table, routing, CRUD, scheduling
Order pricing, invoicing, charts
Filtering, exports, internal notes
YoY comparison charts
Organisation side panel & orders list
Mobile responsive forms
Collections UI + scheduling
Feature flag system for orders
Handover: 10 tickets need reassignment — lease decoupling (#4526) needs special discussion
Konvoy Kegs · Katch Cloud Engineering
3 / 9

## Slide 4
Sprint 3 Velocity — NS Breach Impact
Week 1 lost to NS breach recovery — 12 of 14 closed items were reactive incident work (all Rob)
14
Items Closed
(since Apr 3)
12
Rob's Reactive
NS Fixes
0
Planned Sprint 3
Goals Completed
7
Working Days
Remaining
Sprint Comparison
Sprint 2: 47 items closed in 2 weeks (13 in final week alone)
Sprint 3: Effectively a 1-week sprint for planned work
Key risk: Day 8 scope freeze approaching with zero goal progress
Konvoy Kegs · Katch Cloud Engineering
4 / 9

## Slide 5
Team Load & Current Assignments
Person | Open | Sprint | Focus This Sprint | Status
Rob | 53 | 9 | FL-5, FL-6, NS audit, breach cleanup | Overloaded
Millicent | 30 | 5 | Scheduled order updates, bug fixes, chores | Capacity
Bea | 33 | 12 | FL frontend (blocked), Orders UX tickets | Ramping
Doug | 10 | 7 | All need reassignment before departure | Departing
Unassigned | 49 | — | Includes FL-1 to FL-4 blockers + 28 design tickets | Needs triage
Key issue: Rob has 53 open issues — sustainable is ~22 SP/sprint. Millicent has capacity to absorb FL backend tickets. Bea's 12 sprint items need trimming to 3–4 realistic targets.
Konvoy Kegs · Katch Cloud Engineering
5 / 9

## Slide 6
Quarterly Priorities — Status Check
Fuel Surcharge
Behind
14 tickets total. FL-1 to FL-4 (backend foundation) are unassigned and block everything. Rob's FL-5/FL-6 and all of Bea's frontend work are waiting.
Action: Assign FL-1 to FL-3 to Millicent now
Orders Experience
Progressing
Doug built the core (47 tickets). Bea owns the epic. 28 new design-feedback tickets in backlog need triage. 3 new sub-epics created for UX improvements.
Action: Triage design-feedback batch — pick 3–5 for Sprint 4
Refills in Cloud
Not Started
6 sub-tickets under NS Epic 1. Discovery (#4309) sitting since Sprint 1. Depends on NS Epic 0 Foundation which is also still open.
Action: Rob to complete NS-1.1 discovery this sprint
Konvoy Kegs · Katch Cloud Engineering
6 / 9

## Slide 7
Backlog — 48 Unassigned Items
Natural groupings identified for batch triage:
28
Design Feedback
3 epics: Rentals List, Rental Form, Order Detail. All from design review.
4
NS Audit
Token rotation tasks (#4536-4539). Half-day focused effort.
4
Fuel Levy Backend
FL-1 to FL-4 — critical blockers. Assign to Millicent.
3
Legacy Cleanup
Remove SSID Bank, Sigfox refs, consolidate tenant. Tech debt day.
2
Performance
Global search 11s, assets query. Pair programming session.
7
Other
Misc: cutoff time, unschedule endpoint, billing backpopulate.
Konvoy Kegs · Katch Cloud Engineering
7 / 9

## Slide 8
Doug Handover — Monday Checklist
Must
Confirm all 10 open tickets are documented for Bea to pick up
Must
Deep-dive on #4526 (lease decoupling) — architecturally complex
Must
Rainforest QA test access and credentials documented
Must
Handover recordings confirmed in SharePoint → Development → Recordings
Ask
Undocumented tribal knowledge about Orders frontend state management?
Nice
Group 3 Rainforest QA tickets (#4473-4475) into single effort for Bea
Do
Reassign #4636 (feature flag cleanup) to Bea — good starter ticket
Konvoy Kegs · Katch Cloud Engineering
8 / 9

## Slide 9
Recommended Actions
1
Reassign Doug's 10 tickets — 7 to Bea, 3 QA tickets grouped
2
Assign FL-1 to FL-4 to Millicent — unblock Fuel Levy chain
3
Timebox NS Audit — agree budget (e.g. 3 SP/sprint) with leadership
4
Clean Sprint 1 milestone — move or close 10 stale items
5
Triage design-feedback batch — pick 3–5 for Sprint 4, backlog rest
6
Rob scope reduction — 53 open items unsustainable, defer 10+
7
Revised Sprint 3 goals for remaining 7 days:
Rob: FL-5, FL-6, #4477, #4436, NS-1.1 discovery
Millicent: Start FL-1/FL-2, ship #4586, fix #4567
Bea: First PR merged (#4636 or #4498), start #4565 and #4369
Konvoy Kegs · Katch Cloud Engineering
9 / 9